## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
Milestone 2 - Task 2 | Milestone 2 - Task 2 | US-01 | Research synthetic-user concepts, LLM persona simulation, and behavioral modeling. | SHOULD HAVE | Project scope | Y. Naga Sai Krishna | 2- In Progress
Milestone 2 - Task 2 | Milestone 2 - Task 2 | US-02 | As a researcher, I want the system architecture, agent roles, persona data model, and experiment workflow documented. | MUST HAVE | US-01 | Y. Naga Sai Krishna | 2- In Progress
Milestone 2 - Task 2 | Milestone 2 - Task 2 | US-03 | As a researcher, I want to define product description, target audience, and research objectives in an experiment workspace. | MUST HAVE | US-02 | Y. Naga Sai Krishna | 2- In Progress
Milestone 2 - Task 2 | Milestone 2 - Task 2 | US-04 | As a researcher, I want diverse AI-generated personas with demographic, personality, behavioral, and psychological profiles. | MUST HAVE | US-03 | Y. Naga Sai Krishna | 2- In Progress
Milestone 2 - Task 2 | Milestone 2 - Task 2 | US-05 | As a researcher, I want each persona to retain attributes, opinions, and conversation context across turns. | MUST HAVE | US-04 | Y. Naga Sai Krishna | 2- In Progress
Milestone 2 - Task 3 | Milestone 2 - Task 3 | US-06 | As a researcher, I want to run a survey across all personas and compare responses side-by-side. | MUST HAVE | US-04, US-05 | Y. Naga Sai Krishna | 1- Not Started
Milestone 2 - Task 3 | Milestone 2 - Task 3 | US-07 | As a researcher, I want persona consistency and response realism validated across domains and question types. | MUST HAVE | US-05, US-06 | Y. Naga Sai Krishna | 1- Not Started
Milestone 2 - Task 3 | Milestone 2 - Task 3 | US-08 | As a researcher, I want Survey Mode tested against varied personas and product scenarios. | SHOULD HAVE | US-06, US-07 | Y. Naga Sai Krishna | 1- Not Started
Milestone 2 - Task 3 | Milestone 2 - Task 3 | US-09 | As a researcher, I want to interview a selected persona with memory and consistent in-character responses. | MUST HAVE | US-05 | Y. Naga Sai Krishna | 1- Not Started
Milestone 2 - Task 3 | Milestone 2 - Task 3 | US-10 | As a researcher, I want survey and interview responses analyzed for themes, sentiment, agreement, and trends. | MUST HAVE | US-06, US-09 | Y. Naga Sai Krishna | 1- Not Started
Milestone 2 - Task 3 | Milestone 2 - Task 3 | US-11 | As a researcher, I want a “Would use this product?” score with reasoning for each persona segment. | SHOULD HAVE | US-10 | Y. Naga Sai Krishna | 1- Not Started
Milestone 2 - Task 3 | Milestone 2 - Task 3 | US-12 | As a researcher, I want insight themes and relevance validated across experiment scenarios. | MUST HAVE | US-10, US-11 | Y. Naga Sai Krishna | 1- Not Started
Milestone 2 - Task 4 | Milestone 2 - Task 4 | US-13 | As a researcher, I want a dashboard showing theme clusters, sentiment, persona quotes, and product validation scores. | MUST HAVE | US-10, US-11 | Y. Naga Sai Krishna | 1- Not Started
Milestone 2 - Task 4 | Milestone 2 - Task 4 | US-14 | As a researcher, I want a downloadable PDF report containing persona profiles, response highlights, insights, and validation scores. | MUST HAVE | US-13 | Y. Naga Sai Krishna | 1- Not Started
Milestone 2 - Task 4 | Milestone 2 - Task 4 | US-15 | As a researcher, I want end-to-end testing across all modules before the final project demonstration. | MUST HAVE | US-04, US-06, US-09, US-10, US-13, US-14 | Y. Naga Sai Krishna | 1- Not Started
Note on F1: ====== ID#AAABcShYZQo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
MILESTONE 2 - TASK 2 / TASK 3 / TASK 4 BACKLOG
US-01 | TASK2-T01 | Study synthetic-user research concepts, LLM persona simulation techniques, and behavioral modeling approaches. | 2026-09-15 |  | Y. Naga Sai Krishna | Research | 2- In Progress | 4
US-02 | TASK2-T02 | Document system architecture, agent roles, persona data model, and experiment workflow. | 2026-09-15 |  | Y. Naga Sai Krishna | Design | 2- In Progress | 5
US-03 | TASK2-T03 | Build experiment workspace for product description, target audience, and research objectives. | 2026-09-15 |  | Y. Naga Sai Krishna | Build | 2- In Progress | 6
US-04 | TASK2-T04 | Build Persona Generation Agent for diverse personas with demographic, personality, behavioral, and psychological attributes. | 2026-09-15 |  | Y. Naga Sai Krishna | Coding | 2- In Progress | 8
US-05 | TASK2-T05 | Implement persona memory and consistency across attributes, opinions, and multi-turn conversation context. | 2026-09-15 |  | Y. Naga Sai Krishna | Coding | 2- In Progress | 8
US-06 | TASK3-T01 | Build Survey Mode to collect responses from all personas and display them side-by-side. | 2026-09-26 |  | Y. Naga Sai Krishna | Coding | 1- Not Started | 8
US-07 | TASK3-T02 | Validate persona consistency and response realism across question types and product domains. | 2026-09-26 |  | Y. Naga Sai Krishna | System Test | 1- Not Started | 5
US-08 | TASK3-T03 | Test Survey Mode with varied persona sets and sample product scenarios. | 2026-09-26 |  | Y. Naga Sai Krishna | System Test | 1- Not Started | 5
US-09 | TASK3-T04 | Build Interview Mode with in-character responses and memory across multiple turns. | 2026-09-26 |  | Y. Naga Sai Krishna | Coding | 1- Not Started | 8
US-10 | TASK3-T05 | Develop Insight Extraction Agent for themes, sentiment, agreement patterns, and behavioral trends. | 2026-09-26 |  | Y. Naga Sai Krishna | Coding | 1- Not Started | 8
US-11 | TASK3-T06 | Implement “Would use this product?” scoring with reasoning for persona segments. | 2026-09-26 |  | Y. Naga Sai Krishna | Coding | 1- Not Started | 6
US-12 | TASK3-T07 | Validate insight quality and theme relevance across varied experiment scenarios. | 2026-09-26 |  | Y. Naga Sai Krishna | System Test | 1- Not Started | 5
US-13 | TASK4-T01 | Build Insights and Experiment Results Dashboard for theme clusters, sentiment, persona quotes, and product validation scores. | 2026-10-12 |  | Y. Naga Sai Krishna | Build | 1- Not Started | 8
US-14 | TASK4-T02 | Develop downloadable PDF research report with persona profiles, response highlights, insight summary, and product validation scores. | 2026-10-12 |  | Y. Naga Sai Krishna | Build | 1- Not Started | 8
US-15 | TASK4-T03 | Conduct end-to-end testing of persona generation, Survey Mode, Interview Mode, insight extraction, dashboard, and PDF report. | 2026-10-12 |  | Y. Naga Sai Krishna | Regression Test | 1- Not Started | 8
Planning note: Estimates are planned effort only. Enter actual start/completion dates and daily hours from your work records; update status after confirming progress.
Note on D2: ====== ID#AAABcShYZRI Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on E2: ====== ID#AAABcShYZRU Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on I3: ====== ID#AAABcShYZQ4 Sumeet Kumar Barua08 (2025-01-27 09:44:41) This is the total task estimated in hours for all the user stories
Note on J3: ====== ID#AAABcShYZRc Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 1 work
Note on K3: ====== ID#AAABcShYZRg Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 2 work
Note on L3: ====== ID#AAABcShYZQs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 3 work
Note on M3: ====== ID#AAABcShYZRo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 4 work
Note on N3: ====== ID#AAABcShYZQw Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 5 work
Note on O3: ====== ID#AAABcShYZRk Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 6 work
Note on P3: ====== ID#AAABcShYZRY Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 7 work
Note on Q3: ====== ID#AAABcShYZRA Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 8 work
Note on R3: ====== ID#AAABcShYZRs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 9 work
Note on S3: ====== ID#AAABcShYZRM Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 10 work
Note on T3: ====== ID#AAABcShYZRE Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 11 work
Note on U3: ====== ID#AAABcShYZQ8 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 12 work
Note on V3: ====== ID#AAABcShYZQ0 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 13 work
Note on W3: ====== ID#AAABcShYZRQ Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Milestone 2 - Task 2 | As needed | Potential issue: persona outputs may be repetitive or inconsistent. | Compare persona profiles and multi-turn responses; record the actual issue and fix.
Milestone 2 - Task 3 | As needed | Potential issue: survey/interview outputs or insights may vary across scenarios. | Run sample scenarios and validate response quality, themes, sentiment, and scoring.
Milestone 2 - Task 4 | As needed | Potential issue: dashboard, PDF export, or module integration may fail. | Run end-to-end checks and record actual defects, fixes, and retest results.

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | Milestone 2 - Task 2 | 2026-09-15 |  | Y. Naga Sai Krishna | Document architecture decisions and test persona memory after each change. | Avoid assuming persona consistency without multi-turn checks. | Keep persona attributes, prior answers, and research objectives traceable. | Maintain a repeatable checklist for persona diversity and context retention.
2 | Milestone 2 - Task 3 | 2026-09-26 |  | Y. Naga Sai Krishna | Validate survey/interview behavior across varied personas and product categories. | Avoid treating synthetic responses as verified real-user evidence. | Keep prompts, scenarios, and evaluation criteria consistent. | Record realism and insight-quality test outcomes for each scenario.
3 | Milestone 2 - Task 4 | 2026-10-12 |  | Y. Naga Sai Krishna | Test dashboard visuals, PDF content, and complete workflows. | Avoid marking features complete before export and regression testing. | Keep clear labels that findings are simulated. | Resolve defects, retest fixes, and prepare a final demo checklist.
4
5
6
7