## Task Tracker
Task ID | Milestone | Task Description | Workstream / Type | Assigned To | Status | Action / Next Step | Last Updated | Priority | Remarks | Start Date | End Date
M2-T1 | Milestone 2 | Study synthetic user research concepts, LLM persona simulation techniques, and behavioral modeling approaches. | Research | Project Team | Open | Review literature and examples for synthetic user research, LLM-based persona simulation, and behavioral modeling. Summarize methods, limitations, and evaluation criteria. | 2026-10-21 | Medium | Deliverable: concise research notes and a recommended approach. Ensure synthetic personas are treated as simulated research inputs, not substitutes for validation with real users.
M2-T2 | Milestone 2 | Design system architecture, agent roles, persona data model, and experiment workflow. | Architecture | Project Team | Open | Define system components, agent responsibilities, data flow, persona schema, and experiment lifecycle. Create an architecture diagram and workflow. | 2026-10-21 | Medium | Deliverable: documented architecture, agent-role definitions, persona data model, and experiment workflow reviewed for completeness. | 2026-09-15 | 2026-09-24
M2-T3 | Milestone 2 | Develop experiment workspace where users define product description, target audience, and research objectives. | UI / Workflow | Project Team | Open | Build the experiment setup workspace with fields for product description, target audience, and research objectives. Add input validation and save/load behavior. | 2026-10-21 | Medium | Acceptance criteria: users can create and edit an experiment; required fields are validated; experiment details are available to downstream agents. | 2026-09-26 | 2026-10-10
M2-T4 | Milestone 2 | Build Persona Generation Agent to generate diverse synthetic personas with name, age, occupation, personality traits, behavioral patterns, and psychological profile, displayed as visual persona cards. | Agent Development | Project Team | Open | Implement the Persona Generation Agent and render generated personas as visual cards containing name, age, occupation, personality traits, behavioral patterns, and psychological profile. | 2026-10-21 | Medium | Acceptance criteria: personas are varied, all required fields are displayed, and cards are readable and linked to the correct experiment. | 2026-10-12 | 2026-10-15
M2-T5 | Milestone 2 | Implement Persona Memory and Consistency Module so each persona maintains consistent attributes, opinions, and prior conversation context across multi-turn interactions. | Memory / Consistency | Project Team | Open | Store persona attributes, opinions, and conversation summaries; retrieve relevant context for each new turn and test that responses remain consistent. | 2026-10-21 | Medium | Acceptance criteria: the same persona retains core attributes and prior context across multiple turns; changes in opinion are explainable by new information.
M3-T1 | Milestone 3 | Build Survey Mode: users define questions and all personas generate responses simultaneously, displayed side-by-side for comparison. | Feature Development | Project Team | Open | Create survey question entry and submission flow. Send each question set to all selected personas and display their answers side-by-side. | 2026-10-21 | Medium | Acceptance criteria: all selected personas answer the same questions; responses are clearly labeled by persona and can be compared easily.
M3-T2 | Milestone 3 | Validate persona consistency and response realism across multiple question types and product domains. | Testing / Validation | Project Team | Open | Test personas with open-ended, multiple-choice, preference, and follow-up questions across different product domains. Review realism and consistency against persona profiles. | 2026-10-21 | Medium | Record test cases, inconsistencies, unrealistic answers, and corrective actions. Do not treat simulated responses as evidence of actual customer behavior.
M3-T3 | Milestone 3 | Test Survey Mode across diverse persona sets and product categories using sample experiment scenarios. | Testing | Project Team | Open | Prepare sample experiments for multiple persona groups and product categories. Run Survey Mode, capture outputs, and log failures or unexpected results. | 2026-10-21 | Medium | Deliverable: scenario-based test log covering diverse personas and products, with pass/fail outcomes and issues for follow-up.
M3-T4 | Milestone 3 | Build Interview Mode: conversational interface where users ask questions and a selected persona responds in character, maintaining memory and behavioral consistency across turns. | Feature Development | Project Team | Open | Build a conversational interview interface where the user selects a persona and asks follow-up questions. Pass conversation history and persona memory into each response. | 2026-10-21 | Medium | Acceptance criteria: the selected persona responds in character across multiple turns and maintains relevant context; switching personas does not mix their memories.
M3-T5 | Milestone 3 | Develop Insight Extraction Agent to analyze survey and interview responses and surface recurring themes, sentiment breakdown, agreement patterns, and behavioral trends. | Agent Development | Project Team | Open | Analyze survey and interview responses to extract recurring themes, sentiment, agreement/disagreement, and behavioral trends. Return structured results with supporting response excerpts. | 2026-10-21 | Medium | Acceptance criteria: insights are traceable to source responses, distinguish agreement from disagreement, and avoid presenting unsupported conclusions.
M3-T6 | Milestone 3 | Implement “Would use this product?” scoring, aggregated across persona segments with reasoning per persona group. | Scoring / Analytics | Project Team | Open | Create a “Would use this product?” scoring method. Aggregate results by persona segment and generate a short rationale for each segment score. | 2026-10-21 | Medium | Document scoring scale and aggregation method. Show segment-level results and rationale; label scores as simulated indications rather than real-market forecasts.
M3-T7 | Milestone 3 | Validate insight extraction quality and theme relevance across varied experiment scenarios. | Testing / Validation | Project Team | Open | Evaluate extracted themes and sentiment across varied sample experiments. Compare results with manually reviewed reference themes and adjust extraction rules/prompts. | 2026-10-21 | Medium | Deliverable: validation log documenting theme relevance, missed or false themes, sentiment errors, and improvements made.
M4-T1 | Milestone 4 | Build Insights and Experiment Results Dashboard displaying theme clusters, sentiment breakdown, key persona quotes, and product validation scores visually. | Dashboard / UI | Project Team | Open | Build a dashboard showing theme clusters, sentiment breakdown, representative persona quotes, and product validation scores. Connect visuals to experiment results. | 2026-10-21 | Medium | Acceptance criteria: dashboard sections display the correct experiment data, labels are clear, and quotes/themes can be traced to the relevant responses.
M4-T2 | Milestone 4 | Develop Research Report Generation Module compiling persona profiles, response highlights, insight summary, and validation scoring into a structured downloadable PDF. | Reporting | Project Team | Open | Generate a downloadable PDF containing persona profiles, response highlights, insight summaries, and product validation scores. Check formatting and content completeness. | 2026-10-21 | Medium | Acceptance criteria: PDF downloads successfully, includes all required sections, preserves readable layout, and matches the selected experiment results.
M4-T3 | Milestone 4 | Conduct end-to-end testing across persona generation, both simulation modes, insight extraction, and report generation. | End-to-End Testing | Project Team | Open | Run end-to-end scenarios from experiment setup through persona generation, Survey Mode, Interview Mode, insight extraction, dashboard, and PDF export. Log and resolve defects. | 2026-10-21 | Medium | Deliverable: end-to-end test results and defect log. Confirm core flows work together and retest fixes before sign-off.

## Sheet2
Task Status
Open
In Progress
Blocked
Completed